## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 - Menu Item Management (Staff CRUD) | 5 | Jordan | [7 empty] | Done
Create MenuItem model and schema files |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0 | Done | 3
Implement CRUD controller for menu items |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0 | Done | 2
Create menu items router with all endpoints |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 1
Test menu item endpoints in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 2
User Story #2 - Ingredient Inventory & Low-Stock Alerts | 8 | Jordan | [7 empty] | Done
Create Ingredient and MenuItemIngredient models |  |  | 4 | 2 | 2 | 0 | 0 | 0 | 0 | Done | 1
Implement CRUD controllers for ingredients |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0 | Done | 1
Add low stock alert endpoint to ingredients |  |  | 4 | 0 | 0 | 2 | 2 | 0 | 0 | Done | 1
Test ingredient endpoints and low stock alert |  |  | 3 | 0 | 0 | 0 | 1 | 2 | 0 | Done | 4
User Story #3 - Display Categorized Menu w/ Search & Filter | 5 | Kim | [7 empty] | Done
Add category field and filtering to MenuItem |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 1
Implement search/filter query params in router |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0 | Done | 1
Update read_all controller to support filters |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 1
Test category filtering in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 0
User Story #4 - View Dish Details | 3 | Jordan | [7 empty] | Done
Ensure MenuItem schema includes all detail fields |  |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
Implement read_one endpoint for menu items |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 2
Link ingredients to menu item in response |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 0
Test dish detail endpoint in Swagger UI |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 3
User Story #5 - Guest Checkout (Name, Phone, Address) | 5 | Jordan | [7 empty] | Done
Create Order model with guest fields |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 1
Implement order creation with guest info |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0 | Done | 1
Validate required guest fields in schema |  |  | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 0
Test guest checkout via POST /orders |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 0
User Story #6 - Multiple Payment Methods | 8 | Jordan | [7 empty] | Done
Add payment_method field to Order model |  |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 0
Validate accepted payment methods in schema |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 0 | Done | 0
Update order creation to capture payment method |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 0
Test multiple payment methods in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 0
User Story #7 - Place Order (Takeout/Delivery + Tracking #) | 8 | Jordan/Kim | [7 empty] | Done
Add order_type and tracking_number to Order model |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 0
Auto-generate tracking number on order creation |  |  | 2 | 0 | 2 | 1 | 0 | 0 | 0 | Done | 1
Add order_type validation (takeout/delivery) |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 1
Test order placement and tracking number return |  |  | 1 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 0
User Story #8 - Apply Promotional Code to Order | 3 | Jordan/Kim | [7 empty] | Done
Create PromoCode model and schema |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 1
Link promo_code_id foreign key to Order model |  |  | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 1
Validate promo code on order creation |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 0
Test promo code application in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 0
TOTAL