## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #9 - Real-Time Order Tracking by Order # | 3 | Inthila | [7 empty] | Done
Add read_by_tracking function to orders controller |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Done | 0
Add GET /orders/track/{tracking_number} endpoint |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Done | 2
Test order tracking by tracking number in Swagger UI |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | Done | 3
Verify nested order items returned in response |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 0
User Story #10 - Staff Order Management & Status Updates | 5 | Kim | [7 empty] | Done
Verify OrderUpdate schema includes status field |  |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 1
Add dedicated PUT /orders/{id}/status endpoint |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 0 | Done | 1
Test status transitions in Swagger UI |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | Done | 0
Verify read_all returns full order list for staff |  |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 1
User Story #11 - Chef Order View (Items + Special Instructions) | 3 | Kim | [7 empty] | Done
Verify order response includes nested order_items |  |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 0
Confirm special_instructions field returned per item |  |  | 2 | 0 | 0 | 2 | 0 | 0 | 0 | Done | 1
Test chef view endpoint with special instructions data |  |  | 2 | 0 | 0 | 0 | 2 | 0 | 0 | Done | 3
Add seed data with special instruction examples |  |  | 1 | 0 | 0 | 0 | 0 | 1 | 0 | Done | 1
User Story #12 - Customer Reviews & Ratings | 5 | Inthila | [7 empty] | Done
Verify reviews CRUD endpoints are functional |  |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Done | 2
Add rating validator (1-5) to review schema |  |  | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Done | 1
Add GET /reviews/lowrated endpoint |  |  | 3 | 0 | 0 | 2 | 1 | 0 | 0 | Done | 0
Test reviews and low rated endpoint in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 1
User Story #13 - View Unpopular Dishes & Complaint Analysis | 5 | Inthila | [7 empty] | Done
Add read_low_rated function to reviews controller |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 0
Join reviews with menu items to identify low rated dishes |  |  | 4 | 0 | 2 | 2 | 0 | 0 | 0 | Done | 3
Add GET /reviews/complaints endpoint with dish details |  |  | 3 | 0 | 0 | 0 | 2 | 1 | 0 | Done | 1
Test complaint analysis endpoint in Swagger UI |  |  | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 1
User Story #14 - Promotions & Promo Code Management | 8 | Kim | [7 empty] | Done
Verify promo code CRUD endpoints are functional |  |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 0
Add expiration date validation to promo code creation |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 0 | Done | 3
Add promo code validation on order creation |  |  | 4 | 0 | 0 | 2 | 2 | 0 | 0 | Done | 0
Apply discount to total_price based on discount_percent |  |  | 3 | 0 | 0 | 0 | 1 | 2 | 0 | Done | 1
User Story #15 - Revenue Reporting & Orders by Date Range | 8 | Inthila | [7 empty] | Done
Add read_by_date_range function to orders controller |  |  | 3 | 2 | 1 | 0 | 0 | 0 | 0 | Done | 1
Add GET /orders/daterange?start=&end= endpoint |  |  | 3 | 0 | 2 | 1 | 0 | 0 | 0 | Done | 0
Add GET /orders/revenue?date= endpoint summing total |  |  | 4 | 0 | 0 | 2 | 2 | 0 | 0 | Done | 2
Test revenue and date range endpoints in Swagger UI |  |  | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 1
TOTAL